## Sheet1
# | Code | Description | Estimated Hours | Estimated Completion
1 | plannedJourney.js | Make the addListener "places Changed" into an actual function to save lines of code | 2 | 2018-04-28
2 | plannedJourney.js | Make the map clickable by fixing up the function you just created | 5 | 2018-04-28
3 | plannedJourney.js | Make the data table from clicking in the right location & shown | 3 | 2018-04-29
4 | plannedJourney.js | Line up table / map & fix sizes of the pop ups
5 | plannedJourney.js | Fix numbers cut off at the bottom
6 | plannedJourney.js | Line up map to middle
7 | plannedJourney.html | Have a text div pop up with the address of the place clicked / if thee's only one then it auto fills
8 | plannedJourney.html | Fix headers
9 | plannedJourney.js | Finish submit (Have it Pull the value of the current place pulled up) | 1 | 2018-04-29
10 | plannedJourney.js | Finish back / submit (Hide certain ID / classes) | 1 | 2018-04-29
11 | plannedJourney.js | Finish submit (Grab the actual values from date / Make sure it's > 0 else give a message) | 1 | 2018-04-29
12 | plannedJourney.js | Finish submit (Return to original screen) | 1 | 2018-04-29
13 | plannedJourney.js | Finish submit (Add to table) | 1 | 2018-04-29
14 | plannedJourney.js | Finish dynamic table | 3 | 2018-05-01
15 | plannedJourney.js | Fix up the initial dates / locations including their names | 3 | 2018-05-01
16 | plannedJourney.html | Delete row button
17 | plannedJourney.js | Rating Column
18 | plannedJourney.html | Hints on what is going on
19 | plannedJourney.html | Calculate Itinerary Button
20 | All code | Update Footers / Headers | 7 | 2018-05-03
21 | All Code | Separate code | 7 | 2018-05-05
22 | All code | Comment Code | 1 | 2018-05-05
23 | All code | Start on back end | 0
|  | Total | 36

## Updated-Todo
1 | Redesign entire website based off of Bevy.com (Start from Scratch)
2 | Change rating to priority
3 | Autoclose calendar
4 | One singular search bar / map / make map be in the center
5 | Show calendar dates on other calendar (i.e. if you've already selected start date, show on end date)
6 | Faster load times (Pictures and Mobile)
7 | Make the map not glitchy
8 | Be able to search along routes after itinerary is made for possible crags / gas stations
9 | Move summary of plans so it's not as hard to find
10 | Be able to search by location for things to do around there
11 | Check if add a meal is glitched
12 | Optimize Website (Move JS from top)
13 | All of Zoe's Texts
14 | Make interface more ascetically pleasing
15 | All Josh's Text
16 | Smaller Footer
Have suggestions on searching based on the location
Activity box / popular activities in that area
Dates First
clickMapObject::function(a,b)
a.title

## Update to-do 08-19-2018
Fix About picture & Popular Trips & Planning a Trip / Destinations / Popular Trips
Change the P in the logo to V
Take off Watermarks
Give acknowledgement to Zoe on a page
Allow to build an itinerary like a usual site as opposed to generating an itinerary, just have both options when you want to build a plan i.e. 'I want to build my itinerary day by day' or 'I want to add activities in order to generate an itinerary'
Be able to automatically show activities / plans on the calendar as you're building the day-by-day, and be able to click to enlarge
Create Back End (Stores Username / Password, Calculates Itinerary, Stores Itinerary, Shows Itinerary, Parses Data & Grabs data from internet etc.)
Create database that is capable of saving user names / passwords
Clickable google maps directions based on the calculated itinerary page
Back end to calculate the itinerary
Create database for itineraries
Be able to search along routes after itinerary is made for possible crags / gas stations
Think about new title on Plan a Trip Page
Think about splitting up locations and activities
Pull times from locations in order to correctly generate itinerary based on when they're open
Dynamic clicking on itinerary
Web spiders to parse information for top search locations to put into database for faster loading
Data analytics for pulling information
Database of items necessary based on activities in your trip
Generate itinerary creates a new page where the plan is full page with a map on the bottom with all of the directions from place to place where you can click on legs on either the map or the itinerary to highlight them, see the travel time, change mode of transportation, etc.
Make it able to save websites for ideas to do for each thing on your list
Add calendar to the front page for start / end of your vacation
Be able to click on reviews in order to see reviews
Think of a way to combat fake reviews
Take Saved Trips off of the 'My Account' dropdown until they log in
Have Trip Plans auto load into countries / locations once the actual trip is done
Be able to open calendar and choose #of days to go
Have a filter or warning based on seasons i.e. don't go to Thailand during monsoon season