## Sheet1
# | Code | Description | Estimated Hours | Estimated Completion
1 | plannedJourney.js | Make the addListener "places Changed" into an actual function to save lines of code | 2 | 2018-04-28
2 | plannedJourney.js | Make the map clickable by fixing up the function you just created | 5 | 2018-04-28
3 | plannedJourney.js | Make the data table from clicking in the right location & shown | 3 | 2018-04-29
4 | plannedJourney.js | Line up table / map & fix sizes of the pop ups
5 | plannedJourney.js | Fix numbers cut off at the bottom
6 | plannedJourney.js | Line up map to middle
7 | plannedJourney.html | Have a text div pop up with the address of the place clicked / if thee's only one then it auto fills
8 | plannedJourney.html | Fix headers
9 | plannedJourney.js | Finish submit (Have it Pull the value of the current place pulled up) | 1 | 2018-04-29
10 | plannedJourney.js | Finish back / submit (Hide certain ID / classes) | 1 | 2018-04-29
11 | plannedJourney.js | Finish submit (Grab the actual values from date / Make sure it's > 0 else give a message) | 1 | 2018-04-29
12 | plannedJourney.js | Finish submit (Return to original screen) | 1 | 2018-04-29
13 | plannedJourney.js | Finish submit (Add to table) | 1 | 2018-04-29
14 | plannedJourney.js | Finish dynamic table | 3 | 2018-05-01
15 | plannedJourney.js | Fix up the initial dates / locations including their names | 3 | 2018-05-01
16 | plannedJourney.html | Delete row button
17 | plannedJourney.js | Rating Column
18 | plannedJourney.html | Hints on what is going on
19 | plannedJourney.html | Calculate Itinerary Button
20 | All code | Update Footers / Headers | 7 | 2018-05-03
21 | All Code | Separate code | 7 | 2018-05-05
22 | All code | Comment Code | 1 | 2018-05-05
23 | All code | Start on back end | 0
|  | Total | 36

## Updated-Todo
1 | Redesign entire website based off of Bevy.com
2 | Change rating to priority
3 | Autoclose calendar
4 | Show calendar dates on other calendar (i.e. if you've already selected start date, show on end date)
5 | Faster load times (Pictures and Mobile)
6 | Make the map not glitchy
7 | Be able to search along routes after itinerary is made for possible crags / gas stations
8 | Move summary of plans so it's not as hard to find
9 | Be able to search by location for things to do around there
10 | Check if add a meal is glitched
11 | Optimize Website (Move JS from top)
12 | All of Zoe's Texts
13 | Make interface more ascetically pleasing
14 | All Josh's Text